Lab 5: Monitoring & Controlling based on the PMBOK Guide. This lab focuses on tracking project performance, managing changes, and ensuring alignment with the baseline plans.

### Lab 5: Monitoring & Controlling

#### Objectives:

- Track Project Performance: Students will monitor progress against the schedule and cost baseline using performance measurement techniques.

- Analyze Variances: Students will assess deviations from the plan and calculate key metrics to evaluate project health.

- Manage Changes: Students will handle a hypothetical change request and update project plans accordingly.

#### Lab Content:

- Individual Task: Collect Progress Data

  - Description: Each student gathers hypothetical progress data for 2–3 tasks assigned in Lab 4 (e.g., percentage complete, actual costs).

  - Inputs:

    - Task assignment list and status report from Lab 4.

    - Schedule and cost baseline from Labs 2 and 3.

    - PMBOK Guide (Chapter 4.5: Monitor and Control Project Work).

  - Tools and Techniques:

    - Data collection (assuming task updates, e.g., “UI design 100% complete, cost $600”).

    - Variance analysis (comparing actual vs. planned).

  - Outputs: A short progress update for assigned tasks (e.g., task name, % complete, actual cost, actual duration).

- Group Work (as per classroom theory): Perform Earned Value Analysis

  - Description: Groups aggregate individual progress data and calculate Earned Value Management (EVM) metrics to assess project performance.

  - Inputs:

    - Progress updates from individual task.

    - Schedule and cost baseline from Labs 2 and 3.

    - PMBOK Guide (Chapter 7.4: Control Costs, Chapter 6.6: Control Schedule).

  - Tools and Techniques:

    - Earned Value Management (EVM):

      - Planned Value (PV): Budgeted cost of work scheduled.

      - Earned Value (EV): Budgeted cost of work completed.

      - Actual Cost (AC): Actual cost incurred.

      - Cost Performance Index (CPI) = EV / AC.

      - Schedule Performance Index (SPI) = EV / PV.

    - Spreadsheet calculations.

  - Outputs:

    - An EVM table (e.g., PV = $5,000, EV = $4,500, AC = $5,200).

    - Calculated CPI and SPI (e.g., CPI = 0.87, SPI = 0.90).

    - A brief analysis (e.g., “Project is over budget and behind schedule”).

- Group Work (as per classroom theory): Manage a Change Request

  - Description: Groups process a hypothetical change request (e.g., “Add a new feature: user notifications”) and update project plans.

  - Inputs:

    - WBS, schedule, and cost baseline from previous labs.

    - EVM results from the previous task.

    - PMBOK Guide (Chapter 4.6: Perform Integrated Change Control).

  - Tools and Techniques:

    - Change request evaluation (impact on scope, schedule, cost).

    - Updating baselines (revising WBS, schedule, or budget).

    - Group decision-making (approve or reject the change).

  - Outputs:

    - A change request form (e.g., description, justification, impact: +2 days, +$500).

    - Updated WBS, schedule, or cost baseline reflecting the change.

    - A revised status report incorporating the change.

#### References and Guidelines:

- Primary Reference: PMBOK Guide (latest edition):

  - Chapter 4.5: Monitor and Control Project Work.

  - Chapter 6.6: Control Schedule.

  - Chapter 7.4: Control Costs.

  - Chapter 4.6: Perform Integrated Change Control.

- Supplementary Resources:

  - PMI website (www.pmi.org) for EVM templates and change request forms.

  - Online tutorials on EVM calculations (e.g., YouTube or PMI resources).

  - Sample IT project performance reports.

- Guidelines:

  - Provide simple, instructor-supplied progress data if students struggle with hypothetical updates.

  - Limit the change request to a small scope adjustment to fit lab time.

  - Ensure EVM calculations are verified for accuracy using spreadsheets.

#### Notes:

- Duration: 2–3 hours, with ~1 hour for EVM analysis and ~1 hour for change management.

- Deliverable Submission: Each group submits:

  - EVM table with CPI/SPI and analysis.

  - Change request form and updated plans (WBS, schedule, or cost baseline).

  - Revised status report.

- Instructor Role: Supply a sample change request and progress data, explain EVM formulas, and review outputs for correctness.

- Tools:

  - Excel or Google Sheets for EVM calculations.

  - Word or Google Docs for status reports and change forms.

  - MS Project or Trello (optional) for schedule updates.

### Explanation

Lab 5 emphasizes the monitoring and controlling phase, where students track performance using EVM and adapt to changes, key PMBOK practices. The group work simulates real-time decision-making, preparing students for dynamic project environments. The outputs build on previous labs, ensuring continuity.